**Timeline for Grant Recipients**

|  |  |
| --- | --- |
| **Date / Time** | **Event** |
| Thursday 7 December  1.30pm to 5pm | Community Chest for Social Prescribing Information Day  Barking Learning Centre Conference Centre |
| Monday 8 January 2024  5pm | Deadline for grant applications for the Community Chest |
| Thursday 11 January 2024 | Review grant applications by Steering Group – Confirmation to be sent to successful organisations |
| 8 February 2024 | Participatory Budgeting Event – Barking Learning Centre  10am to 4pm |
| February 2024 | Funding dispersed to organisations |
| March – July 2024 | Activities delivered |
| July 2024 | Monitoring and evaluation workshops with Steering Group and funded organisations |
| August 2024 | Monitoring and evaluation complete  Report written by Steering Group and Council team |
| September 2024 | Appointment of new Steering Group for 2024 – 2025 programme |